## Project Dashboard
Project Overview
Project Name | Agent App
Work order | W01022022
Client | Internal Project
Start Date | 21/02/2022

## Project Estimates
PMID | Defined Goals/Project Milestones | User Story | Total Count | Optimistic | Most Likely | Pessimistic | Man Days | Man hours | Completed Tasks | Billing($) | Mandays per task | Actual Cost($)
PMID001 | Add properties with timer to delete | As an agent I would like to add properties with a specific timer so that it may be deleted when the time is up. | 4 | 3 | 4 | 5 | 4 | 32 | 2 | 480 | 1 | 480
PMID002 | Commission input on New Listing | As an agent I would like to add new listing with specific commission so that other agents may be aware of the incentive on sales | 2 | 2 | 3 | 5 | 3.1667 | 25.3333 | 0 | 0 | 1.5833
PMID003 | Master Account | As an administrator I would like to create a Master Account that enables me to impersonate users and do actions on their behalf. | 4 | 5 | 7 | 10 | 7.1667 | 57.3333 | 0 | 0 | 1.7917
PMID004 | Neighborhood Search Ability | As an agent I would like to search by neighbourhood so that I may be able to look up avaialble properties in the vicinity | 3 | 1 | 2 | 3 | 2 | 16 | 0 | 0 | 0.66667
PMID005 | Street view accessible through map view | As an agent I want a feature to be able to zoom into property and check out the street view so I may be able to view the locality and neighbourhood. | 1 | 1 | 2 | 3 | 2 | 16 | 0 | 0 | 2
PMID006 | Scroll up photo header on listings | As an agent I wish to have the property address and details as static header and a scrollable details view so that I may be able to see the current property details in view. | 2 | 3 | 5 | 7 | 5 | 40 | 0 | 0 | 2.5
PMID007 | Click in photos from header | As an agent I would like to view all photos on a gallery view on right swipe of property details view so that I can quickly swich between details and photos | 2 | 2 | 3 | 5 | 3.1667 | 25.3333 | 0 | 0 | 1.5833
PMID008 | Truncating Description | As an agent I would like to update all descriptions with (Read more/Read less icons) to show a brief of the descriptions in View Property Details and View Buyer Requirements so that more relevant content may not be obscured. | 2 | 2 | 3 | 5 | 3.1667 | 25.3333 | 0 | 0 | 1.5833
PMID009 | Swipe through photos | As an agent I would like view search and see results on map to swipe through all properties on a map by appending a property view, and similar swipe through all photo views on property details so that the agent can quick view all related properties and photos. | 2 | 5 | 10 | 15 | 10 | 80 | 0 | 0 | 5
PMID010 | Notification settings | As an agent I want to have the feauter to turn off push notifications and select email notification interval so that I can select my preference of receiving emails. | 6 | 4 | 7 | 10 | 7 | 56 | 0 | 0 | 1.1667
PMID011 | Skip Add Client Contact Details | As an agent, I would like to add properites or buyer requirements without providing contact details so that I may be able to skip email, messenger or phone contact option. | 8 | 6 | 12 | 18 | 12 | 96 | 0 | 0 | 1.5
PMID012 | Remove User Name field from Sign Up | As a voyage user I wish to remove user name in luie of email address provided as login credential so that username is no longer a requirement for creating an account | 1 | 0.5 | 1 | 1.5 | 1 | 8 | 0 | 0 | 1
PMID013 | Terms of Service in Sign Up Linked incorrectly | As a voyage user I wish to update both ToC and Privacy policy mapped properly so that any ambigutiy is addressed. | 1 | 0.5 | 1 | 1.5 | 1 | 8 | 0 | 0 | 1
PMID014 | Share listing with client | As an agent I wish to have the "Share link" feature so that I may be able to freely share any property with others in the team by email or messenger. | 2 | 2 | 3 | 5 | 3.1667 | 25.3333 | 0 | 0 | 1.5833
PMID015 | Client Tab | As an agent, I want to have a client tab, so that I may be able to see my clients and their associated properties or requirements. | 2 | 3 | 5 | 7 | 5 | 40 | 0 | 0 | 2.5
PMID016 | Add Contacts from Phone | As an agent I need to have the option to import my contacts from my phone so I can associate with properties and requirements. | 2 | 3 | 5 | 7 | 5 | 40 | 0 | 0 | 2.5

## Sprint Planner
PMID | Sprint | Task Id | Task Description | Units Assigned | Start Date | Duration | Status | Completed Date | Job Assignment
Sprint 1 (22-03-2021)
PMID001 |  | T1001 | Create a CRON job to validate active property timers at regular intervals. | 1 | 2022-02-02 | 1 | COMPLETED | 2022-02-03 | Senior Java Developer
PMID001 |  | T1002 | Update property table to create new purge record date-time and update new version of API (New Property/Update Property/View Property) | 1 | 2022-02-02 | 1 | COMPLETED | 2022-02-03 | Senior Java Developer
PMID001 |  | T1003 | Update UI to add property option to purge records if checked on specifed data-time on pages (Add Property/Edit Property/View Property) | 1 | 2022-02-04 |  |  |  | Frontend Developer
PMID001 |  | T1004 | Update UI to update property option to purge records if checked on specifed data-time. | 1 |  |  |  |  | Frontend Developer
Sprint 2
PMID002 |  | T1005 | Update DB with commission_on_sales field, update API (Add Property/Edit Property/View Property) | 1
PMID002 |  | T1006 | Update UI to include commission on sales to (Add Property/Edit Property/View Property pages) | 1
Sprint 3
PMID003 |  | T1007 | Create new Role SuperAdmin | 1
PMID003 |  | T1008 | Create API to swich user and log in activity as superadmin acting as X for every transaction with key signature for auditing. Add API header for impersonated user with superadmin and log to activity. | 1
PMID003 |  | T1009 | Create UI for superadmin account switch user panel with list of users as dropdown. | 1
PMID003 |  | T1010 | Create a UI header tag SuperAdmin (X User) if impersonation is active. | 1
Sprint 4
PMID004 |  | T1011 | Create search API to search by neighbour hood (keyword match) | 1
PMID004 |  | T1012 | Identify if neighbourhood or keyword search is suppored by MLS and integrate the same | 1
PMID004 |  | T1013 | Update UI to allow new search by Neighbourhood (cosmetic chages to labels) | 1
Sprint 5
PMID005 |  | T1014 | Map view to include integration with street view on property popup or street view marker in popup. | 1
Sprint 6
PMID006 |  | T1015 | In View Property Details add Header and scrollable content view | 1
PMID006 |  | T1016 | In View Buyer Requirement Details add Header and scrollable content view | 1
Sprint 7
PMID007 |  | T1017 | Create new right swipe gallery section in property details view | 1
PMID007 |  | T1018 | Create a new gallery to show thumbnails of all photos with click to view option. | 1
Sprint 8
PMID008 |  | T1019 | Update property detail view descriptions with script to handle read more/read less based on content length | 1
PMID008 |  | T1020 | Update buyer requirement view descriptonis with script to handle read more/read less based on content length | 1
Sprint 9
PMID009 |  | T1021 | Update map view with images of properties in the current view which can be swiped though the image area below the map | 1
PMID009 |  | T1022 | Update property details view with all photos loaded in the image view that can be swiped to the next consequtive image of the property | 1
Sprint 10
PMID010 |  | T1023 | Create a mail_notification table and add mailing_interval_preference (daily/weekly/monthly) in contact table | 1
PMID010 |  | T1024 | Remove current email dispatch function and replace with store email to email_digest table | 1
PMID010 |  | T1025 | Create a Cron job to check schdule and dispatch email based on preference (daily/weekly) | 1
PMID010 |  | T1026 | Create a new field is_push_notification_enabled in contact table | 1
PMID010 |  | T1027 | Update current push notification model to validate if push_notificaiton is enabled before posting | 1
PMID010 |  | T1028 | In UI user profile create new push_notification and mail_interval_presence fields and also update the same in registration forms and add client screens | 1
Sprint 11
PMID011 |  | T1029 | Update add contact table to make email and phone optional in Add Property/Update Property - Client tab | 1
PMID011 |  | T1030 | Update View property details screen and show call/text/email only if client details are present or for other users, primary agent details are displayed | 1
PMID011 |  | T1031 | Display contact phone/email/message on list my properties card view only when present | 1
PMID011 |  | T1032 | Update add contact table to make email and phone optional in Add/Update Buyer Requirement - Client tab | 1
PMID011 |  | T1033 | Update View Buyer Requirement screen and show call/text/email only if client details are present or for other users, primary agent details are displayed | 1
PMID011 |  | T1034 | In Matched properties view, disable email, request site visit to be enabled only if client details are present | 1
PMID011 |  | T1035 | In search view, remove contact details of own properties in search if the client details are not present. | 1
PMID011 |  | T1036 | In link new properties, search view do likewise. | 1
Sprint 12
PMID012 |  | T1037 | Remove username field in registration form, no changes will be requried (the username is permenant/emails can change over time) login is already changed to email, no other update required) | 1
Sprint 13
PMID013 |  | T1038 | Update ToC & Privacy Policy links on Registration form and in the app. | 1
Sprint 14
PMID014 |  | T1039 | Create an API to share properties on Voyage or MLS | 1
PMID014 |  | T1040 | For UI add social media share plugin to share content and include in all property card/view property details pages | 1
Sprint 15
PMID015 |  | T1041 | Create Client Tab as Contacts, on clicking any contact show both buyer requirements/properties on offer | 1
PMID015 |  | T1042 | Update API changes to existing client listing. | 1
Sprint 16
PMID016 |  | T1043 | Create API to import phone contact to contacts table | 1
PMID016 |  | T1044 | Use react native module to import phone contacts, in profile add Sync Contacts on phone option. | 1

## Resources
# | Resource Name | Resource Type | Designation | Assigned Tasks | Current Tasks | Completed Tasks
1 | Architect | STAFF | Architect | 0 | 0 | 0
2 | Senior Java Developer | STAFF | AWS Senior Engineer | 2 | 0 | 2
3 | Frontend Developer | STAFF | React Native Developer | 2 | 0 | 0
4 | UX Designer | STAFF | Designer | 0 | 0 | 0
5 | Test Engineer | CONTRACTOR | App Tester

## Helpers
Project Status | Cost per Hour ($) | Resource Type
IN-PROGRESS | 30 | STAFF
ON-HOLD |  | CONTRACTOR
CANCELLED |  | AGENCY
WITHDRAWN
COMPLETED